## Sheet1
Action ID # | Issue/Action Item | Responsible | Assigned Date | Date Due | Status | Notes
1 | Tech personnel was unable to integrate vendor's request. Incompatabilities in software hardware integration. | Infrastructure Manager | 2018-08-07 | 2018-08-11 | Open - in progress | 8/8/2018: developed test environment and contacted vendor for test and it failed. Additional hardware required. 8/12/2018: Support hardware arrived. Being installed.
2
3
4
5
Objectively state the issue, and what the desired outcome is (e.g., agreement on xx, fulfillment of data request by x/x/xx).
This person is responsible for identifying issues, assigning for resolution, monitoring for completion, and closing issues.

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only