## Sheet1
EARNED VALUE STATUS REPORT
Project Title: |  | Date Prepared:
Budget at Completion (BAC): |  | Overall Status:
| Current Reporting Period | Current Period Cumulative | Past Period Cumulative
Planned value (PV)
Earned value (EV)
Actual cost (AC)
Schedule variance (SV)
Cost variance (CV)
Schedule performance index (SPI)
Cost performance index (CPI)
Root Cause of Schedule Variance:
Impact on Deliverables, Milestones, or Critical Path:
Root Cause of Cost Variance:
Impact on Budget, Contingency Funds, or Reserve:
Percent planned
Percent earned
Percent spent
Estimates at Completion (EAC):
EAC w/CPI [BAC/CPI]
Selected EAC, Justification, and Explanation
To complete performance index (TCPI)

## Sheet2
Parametric Estimates
WBS ID | Effort Hours | Resource Quantity | % available | Performance factor | Duration Estimate
1.1 | 150 | 2 | 75% | 80% | 125
Analogous Estimates
WBS ID | Prior activity | Prior Variable | Duration | Current variable | Multiplier | Duration Estimate
1.1 | Build deck | 160 sq. ft. | 10 days | 200 sq. ft. | 1.25 | 12.5
Three Point Estimates
WBS ID | Optimistic estimate | Most likely estimate | Pessimistic estimate | Weighting factor | Expected Duration Estimate
1.1 | 20 | 25 | 36 | (o+4m+p)/6 | 26